## MO 606-2025
MO 606 Continuum of Care Annual Requirements Calendar-2025
ACTIVITY | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
CoC Notice of Funding Opportunity
CoC Bi-Annual Registration | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: 2nd Tuesday of January thru 1st Thursday of March
GIW Review and Approval | MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: GIW Review, Change Forms, and Approval to CPD
New/Renewal Scorecards | MO 606 Continuum of Care Annual Requirements Calendar-2025 may: NOFO New/Renewal Scorecards
Reallocation/Funding Policies Review | MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: Review of CoC's Funding Policies/Project Spending
Review/Scoring/Ranking | MO 606 Continuum of Care Annual Requirements Calendar-2025 aug: Review/Ranking Committee Convenes
HUD Competition Period | MO 606 Continuum of Care Annual Requirements Calendar-2025 jun: NOFO posted/ARD released Local Competition; MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: Consolidated Application DUE **
CoC Bi-Annual Renewal Process** | MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: GIW Review and Approval; MO 606 Continuum of Care Annual Requirements Calendar-2025 jul: Local Process Renewal and Reallocation DUE**
MHDC Annual HESP RFA
HESP Request for Applications | MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: RFA posted and DUE 3/31/2025
HMIS/HUD Reporting | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: Quarterly APRs; MO 606 Continuum of Care Annual Requirements Calendar-2025 apr: Quarterly APRs; MO 606 Continuum of Care Annual Requirements Calendar-2025 jul: Quarterly APRs; MO 606 Continuum of Care Annual Requirements Calendar-2025 oct: Quarterly APRs
Longitudinal System Analysis | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: LSA DUE; MO 606 Continuum of Care Annual Requirements Calendar-2025 nov: LSA Opens; MO 606 Continuum of Care Annual Requirements Calendar-2025 dec: LSA data clean
System Performance Measures | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: SPM data clean; MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: SPM DUE **; MO 606 Continuum of Care Annual Requirements Calendar-2025 nov: SPM Opens
PIT and HIC | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: PIT Count; MO 606 Continuum of Care Annual Requirements Calendar-2025 feb: PIT Data Review; MO 606 Continuum of Care Annual Requirements Calendar-2025 apr: PIT/HIC DUE **; MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: PIT Pre-planning; MO 606 Continuum of Care Annual Requirements Calendar-2025 oct: PIT/HIC Planning
MO 606 Planning Grant | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: Start 1/1/2025; MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: APR due; MO 606 Continuum of Care Annual Requirements Calendar-2025 dec: End 12/31/2025
MO 606 HMIS Grants | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: HMIS YHDP APR; MO 606 Continuum of Care Annual Requirements Calendar-2025 jul: HMIS CoC APR; MO 606 Continuum of Care Annual Requirements Calendar-2025 dec: HMIS SNOFO APR
HMIS Lead Evaluation | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: CoC Board Conducts HMIS Lead Evaluation
MO 606 Annual Requirements
Written Standards Review | MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: Policy and Planning Committee Convenes
Coordinated Entry Policy | MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: Coordinated Entry Committee
CoC Governance Charter Review | MO 606 Continuum of Care Annual Requirements Calendar-2025 feb: Review; MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: CoC Approval; MO 606 Continuum of Care Annual Requirements Calendar-2025 may: Review; MO 606 Continuum of Care Annual Requirements Calendar-2025 jun: CoC Approval; MO 606 Continuum of Care Annual Requirements Calendar-2025 nov: Review; MO 606 Continuum of Care Annual Requirements Calendar-2025 dec: CoC Approval
CoC Conflict of Interest Certification | MO 606 Continuum of Care Annual Requirements Calendar-2025 jun: Annual COI
CE Annual Evaluation | MO 606 Continuum of Care Annual Requirements Calendar-2025 apr: **Coordinated Entry/Performance Committee Convenes
Needs and Gaps Analysis | MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: Needs/Gaps Analysis Planning; MO 606 Continuum of Care Annual Requirements Calendar-2025 oct: Needs and Gaps/Data Collection/Analysis/Report
Grantee Monitoring/Housing First Assessment | MO 606 Continuum of Care Annual Requirements Calendar-2025 feb: Housing First Assessment; MO 606 Continuum of Care Annual Requirements Calendar-2025 may: Housing First Review/Grantee Risk Assessment; MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: Grantee Monitoring
Collaborative Applicant Evaluation | MO 606 Continuum of Care Annual Requirements Calendar-2025 jan: CoC Board Conducts CA Evaluation
Annual Trainings **
VAWA and Confidentiality | MO 606 Continuum of Care Annual Requirements Calendar-2025 dec: VAWA
Fair Housing/Anti-Discrimination | MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: FHA/Discrimination
Mainstream Benefits | MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: Mainstream Benefits
Housing First | MO 606 Continuum of Care Annual Requirements Calendar-2025 jun: Housing First
MO 606 Ongoing Trainings
Care Coordination/Trauma Care
Coordinated Access and Entry
MO 606 Membership and Governing Board
CoC Membership | MO 606 Continuum of Care Annual Requirements Calendar-2025 mar: Membership Meeting; MO 606 Continuum of Care Annual Requirements Calendar-2025 jun: Membership Meeting/At-Large Election; MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: Membership Meeting; MO 606 Continuum of Care Annual Requirements Calendar-2025 oct: Regional Elections; MO 606 Continuum of Care Annual Requirements Calendar-2025 dec: Membership Meeting/At-Large Election
CoC Governing Board | MO 606 Continuum of Care Annual Requirements Calendar-2025 apr: Review CA/HMIS Lead Evaluations; MO 606 Continuum of Care Annual Requirements Calendar-2025 may: At-Large Request for Application; MO 606 Continuum of Care Annual Requirements Calendar-2025 sep: Request for Committee Work Plans; MO 606 Continuum of Care Annual Requirements Calendar-2025 oct: At-Large Request for Application; MO 606 Continuum of Care Annual Requirements Calendar-2025 nov: Committee Work Plans Approved
** Subject to Change | jan | feb | mar | apr | may | jun | jul | aug | sep | oct | nov | dec
Missouri Balance of State (MO 606) Annual Requirements Calendar-2025